## Sheet1
Activity | Status | time | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21
Optimizing fill bucket | Not started | 1 week | bar: Week 12
Infinite scrolling | Not started | 1 week | bar: Week 13
Full screen mode | Not started | 2 days | bar: Week 14
Grab and move elements tool | Not started | 2 days | bar: Week 15
Any other tools I can think of | Not started | 3 weeks | bar: Week 16 to Week 18
Bug fixing/testing | In progress | 4 weeks | bar: Week 10; Week 19 to Week 21
optimizing user experience | Not started | 3 week | bar: Week 19 to Week 21
Fill bucket tool | Complete | 4-5 hours | bar: Week 10
Rectangle tool | Complete | 1 day | bar: Week 6
Make ellipse tool | Complete | 1 day | bar: Week 6
Moveable line tool | Complete | 1 day | bar: Week 6
Scissor tool | Complete | 1 day | bar: Week 6
Stamp tool | Complete | 1 day | bar: Week 6